## Sheet1
Epic | User Story | Sprint | Estimate | Priority | Status | Notes
EPIC 1: Capture & Transcription | As a therapist, I want to record a session from mobile/desktop. | Sprint 1 | 8 hrs | 1 | To Do
EPIC 1: Capture & Transcription | As a therapist, I want accurate transcription cleaned of filler words. | Sprint 1 | 12 hrs | 1 | To Do
EPIC 1: Capture & Transcription | As a therapist, I want mobile audio upload with fallback offline transcription. | Sprint 1 | 10 hrs | 2 | To Do
EPIC 2: Dual-Mode Notes | As a therapist, I want to toggle between SOAP-style and narrative formats. | Sprint 2 | 10 hrs | 2 | To Do
EPIC 2: Dual-Mode Notes | As a therapist, I want format preference saved per patient. | Sprint 2 | 6 hrs | 3 | To Do
EPIC 2: Dual-Mode Notes | As a therapist, I want to preview and edit notes before finalizing. | Sprint 2 | 8 hrs | 2 | To Do
EPIC 3: Insight Extraction | As a therapist, I want recurring emotional themes auto-highlighted. | Sprint 3 | 12 hrs | 1 | To Do
EPIC 3: Insight Extraction | As a parent, I want a 2-sentence summary of my child’s sessions. | Sprint 3 | 6 hrs | 3 | To Do
EPIC 3: Insight Extraction | As a therapist, I want strong emotions and peaks flagged. | Sprint 3 | 10 hrs | 2 | To Do
EPIC 4: Security & Compliance | As a user, I want end-to-end encryption (TLS + AES). | Sprint 4 | 6 hrs | 1 | To Do
EPIC 4: Security & Compliance | As a user, I want a built-in consent workflow. | Sprint 4 | 8 hrs | 1 | To Do
EPIC 4: Security & Compliance | As a user, I want PHI to be automatically redacted before storage. | Sprint 4 | 10 hrs | 1 | To Do
EPIC 5: Per-Patient Notebook | As a therapist, I want a digital notebook per patient. | Sprint 5 | 8 hrs | 2 | To Do
EPIC 5: Per-Patient Notebook | As a therapist, I want free-text notes saved in the notebook. | Sprint 5 | 6 hrs | 3 | To Do
EPIC 5: Per-Patient Notebook | As a therapist, I want session entries auto-linked to the right patient. | Sprint 5 | 8 hrs | 2 | To Do
EPIC 6: Customization & Bilingual UX | As a user, I want bilingual support (EN/HE). | Sprint 6 | 10 hrs | 2 | To Do
EPIC 6: Customization & Bilingual UX | As a therapist, I want to adjust output style to SOAP/narrative mix. | Sprint 6 | 10 hrs | 2 | To Do
EPIC 6: Customization & Bilingual UX | As an org, I want department-level template enforcement. | Sprint 6 | 12 hrs | 1 | To Do