## Detailed Backlog
Epic | User Story | Sprint | Estimate | Priority | Status | Notes | Estimate_Hours
EPIC 1: Capture & Transcription | As a therapist, I want to record a session from mobile/desktop. | Sprint 1 | 20.0 hrs | 1 | Missed |  | 20
EPIC 1: Capture & Transcription | As a therapist, I want accurate transcription cleaned of filler words. | Sprint 1 | 30.0 hrs | 1 | Done |  | 30
EPIC 1: Capture & Transcription | As a therapist, I want mobile audio upload with fallback offline transcription. | Sprint 1 | 25.0 hrs | 2 | Done |  | 25
EPIC 2: Dual-Mode Notes | As a therapist, I want to toggle between SOAP-style and narrative formats. | Sprint 2 | 25.0 hrs | 2 | Done |  | 25
EPIC 2: Dual-Mode Notes | As a therapist, I want format preference saved per patient. | Sprint 2 | 15.0 hrs | 3 | Missed |  | 15
EPIC 2: Dual-Mode Notes | As a therapist, I want to preview and edit notes before finalizing. | Sprint 2 | 20.0 hrs | 2 | Done |  | 20
EPIC 3: Insight Extraction | As a therapist, I want recurring emotional themes auto-highlighted. | Sprint 3 | 30.0 hrs | 1 | To Do |  | 30
EPIC 3: Insight Extraction | As a parent, I want a 2-sentence summary of my child’s sessions. | Sprint 3 | 15.0 hrs | 3 | To Do |  | 15
EPIC 3: Insight Extraction | As a therapist, I want strong emotions and peaks flagged. | Sprint 3 | 25.0 hrs | 2 | To Do |  | 25
EPIC 4: Security & Compliance | As a user, I want end-to-end encryption (TLS + AES). | Sprint 4 | 15.0 hrs | 1 | To Do |  | 15
EPIC 4: Security & Compliance | As a user, I want a built-in consent workflow. | Sprint 4 | 20.0 hrs | 1 | To Do |  | 20
EPIC 4: Security & Compliance | As a user, I want PHI to be automatically redacted before storage. | Sprint 4 | 25.0 hrs | 1 | To Do |  | 25
EPIC 5: Per-Patient Notebook | As a therapist, I want a digital notebook per patient. | Sprint 5 | 20.0 hrs | 2 | To Do |  | 20
EPIC 5: Per-Patient Notebook | As a therapist, I want free-text notes saved in the notebook. | Sprint 5 | 15.0 hrs | 3 | To Do |  | 15
EPIC 5: Per-Patient Notebook | As a therapist, I want session entries auto-linked to the right patient. | Sprint 5 | 20.0 hrs | 2 | To Do |  | 20
EPIC 6: Customization & Bilingual UX | As a user, I want bilingual support (EN/HE). | Sprint 6 | 25.0 hrs | 2 | To Do |  | 25
EPIC 6: Customization & Bilingual UX | As a therapist, I want to adjust output style to SOAP/narrative mix. | Sprint 6 | 25.0 hrs | 2 | To Do |  | 25
EPIC 6: Customization & Bilingual UX | As an org, I want department-level template enforcement. | Sprint 6 | 30.0 hrs | 1 | To Do |  | 30

## Sprint Summary
Sprint | Sprint Workload (hrs) | Cumulative Remaining Work | Sprint Number | Target Velocity (hrs/sprint) | Remaining Work (Simulated) | Actual Velocity (hrs) | Remaining Work (Real World)
Sprint 1 | 75 | 400 | 1 | 45 | 352.5 | 55 | 345
Sprint 2 | 60 | 325 | 2 | 45 | 308.2 | 45 | 300
Sprint 3 | 70 | 265 | 3 | 45 | 260 | 0 | 300
Sprint 4 | 60 | 195 | 4 | 45 | 207.4 | 0 | 300
Sprint 5 | 55 | 135 | 5 | 45 | 163.6 | 0 | 300
Sprint 6 | 80 | 80 | 6 | 45 | 119.8 | 0 | 300