## Sheet1
Epic | User Story | Sprint | Status | Notes
EPIC 1: Capture & Transcription | As a therapist, I want to record a session from mobile/desktop. | Sprint 1 | Done
EPIC 1: Capture & Transcription | As a therapist, I want accurate transcription (Whisper/GSTT) cleaned with filler removal. | Sprint 2 | In Progress
EPIC 2: Dual-Mode Notes (Progress + Process) | As a therapist, I want to toggle between SOAP-style and narrative note formats. | Sprint 2 | To Do
EPIC 2: Dual-Mode Notes (Progress + Process) | As a therapist, I want my preferred note format saved per patient. | Sprint 2 | To Do
EPIC 3: Insight Extraction | As a therapist, I want recurring themes/emotions auto-extracted from notes. | Sprint 1 | Done
EPIC 3: Insight Extraction | As a parent, I want a short summary of my child’s therapy progress. | Sprint 2 | To Do
EPIC 4: Security & Compliance | As a user, I want my data encrypted (in transit + at rest). | Sprint 1 | Done
EPIC 4: Security & Compliance | As a user, I want to explicitly approve data capture via a consent workflow. | Sprint 1 | Missed | Carry over to next sprint
EPIC 5: Per-Patient Notebook | As a therapist, I want notes to auto-attach to each patient’s notebook. | Sprint 2 | To Do
EPIC 5: Per-Patient Notebook | As a therapist, I want to add free-text comments post-session. | Sprint 2 | To Do
EPIC 6: Bilingual UX (HE/EN) | As a Hebrew-speaking therapist, I want a localized UI. | Sprint 2 | To Do
EPIC 6: Bilingual UX (HE/EN) | As a user, I want quick-insert goals/outcomes checkboxes. | Sprint 2 | To Do
EPIC 7: Customization Engine | As a therapist, I want to customize note output format (SOAP/narrative mix). | Sprint 2 | To Do
EPIC 7: Customization Engine | As an org, I want templates enforced at department level. | Sprint 2 | To Do