## Sheet1
Sprint | Epic | Story | Estimate (days) | Priority
Sprint 3 | Website Infrastructure | Set up front-end repo with routing + Tailwind | 2 | High
Sprint 3 | Website Infrastructure | Implement homepage layout with placeholders | 2 | High
Sprint 3 | Product Preview | Build fake endpoint for One-Tap Dictation → Note | 2 | High
Sprint 4 | Website Infrastructure | Implement consent flow & HIPAA messaging block | 2 | Medium
Sprint 4 | Feature Preview | Connect session-to-note demo to actual transcription logic | 3 | High
Sprint 4 | Website Integration | Support marketing with screenshot/copy upload interface | 1.5 | Medium
Sprint 5 | Website Integration | Enable bilingual toggle (EN/HE) on landing page | 1.5 | Medium
Sprint 5 | Website QA | QA all marketing copy against final layout | 1.5 | Medium
Sprint 5 | User Feedback Loop | Embed feedback form + GTM tags on site | 1 | Low