## Sheet1
Sprint | Epic | Story | Estimate (days) | Priority
Sprint 1 | Website Launch Readiness | Refine product messaging with engineering | 2 | High
Sprint 1 | Website Launch Readiness | Draft homepage hero, subhead, and CTAs | 1.5 | High
Sprint 1 | Case & Asset Prep | Develop 1-pager product overview (PDF) | 2 | Medium
Sprint 2 | Website Launch Readiness | Write feature pillar blurbs (capture, redact, export) | 2 | High
Sprint 2 | Demand Generation | Create LinkedIn teaser campaign (3 posts) | 1.5 | Medium
Sprint 2 | Case & Asset Prep | Storyboard 60s ‘How It Works’ video | 2.5 | Medium
Sprint 3 | Website Launch Readiness | Finalize website structure + upload content | 2 | High
Sprint 3 | Demand Generation | Launch ‘Start Your Pilot’ email campaign | 1.5 | High
Sprint 3 | Case & Asset Prep | Write anonymized sample note (before/after) | 1.5 | Medium